## Sheet1
S.No | Issue faced | Action taken | Staus
1 | Stack over flow and restarting the ESP32 | Debugging the Libraries and pre built functions in firmware | Resolving
2 | Supply Chain Problem for parts | Contacted Quectel and booked 500 units for production in 2023 | Resolved
3 | GSM and GPS devices not working in AU | Contacted Quectel and got the firmware of modules updated to recognize Telstra and other operators in AU | Resolved
4 | Cold start of GPS taking too much time | Upgraded the Module firmware with support from Quectel | Resolved
5 | PCB fabrication using PCIE module | Upgraded the design to remove PCIE as the PCB will be used in construction machinery and may face vibrations. | Resolved
6 | GSM and GPS module stability testing with Noisy power supplies | Initial testing failed and then redesign was carried out. | Resolved
7 | Device provisioning on IOT HUB | Still trying to get it done but device restarts due to firmware issues, however the successful attempt was made to get device registered on IOT Hub using WIFI and symatic key | Momentory on hold
8 | Posting data on IOT HUB and reading back the data like Employee ID, working hours etc | couldn't get it done with out Device provisioning | not tested yet.